## Sheet1
Sr. No | Date of Request. | Mont | Changes | Email subject/Changes on panel | Requirment | Possibility | Comment | MandaysEfforts | Approval | Date of Approval. | Billing Man days | Payment
1 | 2025-07-05 | 2025-05-01 | UI and Backend | usersummaryreport, cerfgsadmin(Changes in vendor summary report) | Category wise connect traffic on email | yes |  | 15 | yes | 2025-07-05
2 | 2025-07-05 | 2025-05-01 | UI and Backend | usersummaryreport, cerfgsadmin(Single email containing few users details at reseller level and for few as individual users) | Reseller summary of user on email reports was changed, as user wise done for better traffic reviewing | Yes |  | 10 | yes | 2025-07-05
3 | 7/23/2025 | 2025-07-01 | UI | API document changes for CRID (Update API DOC on CRID Panel) | API's were updated in the provided document | Yes |  | 7 |  | 7/23/2025
4 | 7/28/2025 | 2025-07-01 | UI and Backend | Message type PM/UC in detailed report( Encoding Type column Required in Detailed Report) | Changes to show plain message and unicode message in detailed report | Yes | No approval for this | 6 |  | 7/28/2025
5 | 7/28/2025 | 2025-07-01 | UI and Backend | Template ID-wise routing | New Application Code Development and changes | Yes |  | 330 |  | 2025-07-10 |  |  | 118
6 | 7/30/2024 | 2024-07-01 | Custum Application |  | New Application development | Yes | New application was developed for the Ramco and deployed on Ramco servers | 90 |  | 2025-12-08
7 | 7/30/2024 | 2024-07-01 | Backend | New Entity ID and Sender ID Implementation ¦¦ Ramco Cement | New table was made by ramco due to which backed changes were done in the table format | yes | Re-deployement for the new table format | 2 | yes | 2025-12-08
8 | 2025-08-08 | 2025-08-01 | UI and Backend | KTK reporting- developed latency report and deployed in Mysql server (Latency Report April 2025 Dated 21-8-25) | Changes were made in UI for OTP and Trans as per cerf team reuirement | Yes |  | 3 |  | 2025-08-08
9 | 2025-11-08 | 2025-08-01 | UI and Backend | Approver + Margin page | New architectural development with application development too. | Yes |  | 8
10 | 8/14/2025 | 2025-08-01 | Backend | CRID changes of login from User ID to email | User login encription changed from email to User ID , now can login from both User ID and email | yes | No effort mentioned | 4 |  | 2025-08-19
11 | 8/18/2025 | 2025-08-01 | UI and Backend | CRID-invoice format changed 7 times (Multiple times chnages done in invoice and billing module ) Mail - Implementation of crid changes | Multiple times changes in alligment, information , addrress , desgnation etc. | Yes |  | 12 |  | 8/18/2025
12 | 8/25/2025 | 2025-08-01 | UI | Update on Invoicing Address ¦ CRID | Address changes done in invocie | yes |  | 1 | yes | 8/25/2025
13 | 2025-01-09 | 2025-09-01 | UI and Backend | Requirement for detail report (Clicker report on RCS panel ) | RCS clicker report of all campiagns . | yes | Done deployed | 5 | Yes | 2025-03-09 |  | Yes
14 | 2025-08-09 | 2025-09-01 | API chnages | Request for GET API | Requirement for GET API for all API to be changed from POst to get | Yes | no approval | 4 |  | 2025-08-09
15 | 2025-02-10 | 2025-10-01 | UI and Backend | Template-ID-wise summary page (Template ID-wise Summary Deployment) | Template ID wise count mentioned on UI | Yes | New template id wise summary page developed | 7 |  | 2025-02-10
16 | 2025-03-10 | 2025-10-01 | UI and Backend | Mtalk data and consolidated report | New UI was developed for M-talk | Yes |  | 5 | yes | 2025-03-10
17 | 2025-03-10 | 2025-10-01 | UI and Backend | Latency Report for KTK and KTK data | Latency page for OTP and TRans , KTK data Inserted on server from March 2024 to september 2025 | Yes | No approval on mail for 25 days mentioned in last email by abhishek | 20 | yes | 2025-03-10
18 | 2025-07-10 | 2025-10-01 | UI | MoneyTap integration | Operational calls with client for multiples times | Yes |  | 4 |  | 2025-07-15
19 | 10/27/2025 | 2025-10-01 | Backend | OASYS user delivery callback for YYYY-MM-DD (DLR Format Customization Request - OASYS) | Format changes for callback send to CRM tool of OASYS team | Yes |  | 8 | yes | 10/27/2025
20 | 10/30/2025 | 2025-10-01 | API changes | many to many api -> | API developed and integrated with webhook | Yes |  | 6 | yes | 10/30/2025
21 | 10/31/2025 | 2025-10-01 | OPerational | Enterprise connect for VMSC (Enterprise Connect) | VMSC connect were created for enterprise | Yes |  | 2 |  | 10/31/2025
22 | 10/31/2025 | 2025-10-01 | APi changes | Api paramater change request | Pramater changes | Yes | no approval | 5 |  | 10/31/2025
23 | 2025-11-11 | 2025-11-01 | UI and Backend | RCS VMSC | New components developed for VMSC for on RCS | Yes |  | 37 |  | 2025-11-11
24 | 11/17/2025 | 2025-11-01 | UI and Backend | Webhook Configuration armsoft -> New webhook configuration for Many to many api | Clinet specific Webhook was developed and API was developed | Yes |  | 6 | yes | 11/17/2025
25 | 11/20/2025 | 2025-11-01 | UI and Backend | Moneytap error report | Error wise summary report | Yes | no approval | 3 |  | 11/20/2025
26 | 11/20/2025 | 2025-11-01 | UI and Backend | moneytap blacklist feature | data base upload upto 50 lakh number and functionality changes | Yes | no approval | 13 |  | 11/20/2025
27 | 11/27/2025 | 2025-11-01 | UI and Backend | Voice campaign data | Voice campaign data | Yes |  | 28 |  | 11/27/2025
28 | 11/27/2025 | 2025-11-01 | UI | Crid- invoice change for proforma (Implementation of crid requested changes ) | Name changes in Invoice genertation | Yes | Gaurav sir asked for confirmation from abhishek | 2 | yes | 11/27/2025 |  |  | Column1
29 | 2025-10-12 |  | Backend | EDCS: Requesting detailed report-CCBMTC | detailed report for user CCBMTC for April 2025 and May 2025. |  |  | 7
30 | 2025-10-12 |  | UI and Backend | Payment mode Postpaid to Prepaid - KTK | KTK , postpaid to prepaid. | Yes
31 | 12/17/2025 |  | Backend | Moneytap DND data | DND data for 45 days. |  |  | 5
32
33 | 2026-05-01 |  | UI and Backend | Re: Final requirement ¦¦ OASYS | timestamp search, live filtering, and real-time downloads | Yes |  | 4 | Yes | 2026-09-01
34 | 2025-09-11 |  | Learning_spiral Data | last 1 year data prepared and shared to team
35 | 2025-12-09 |  | Application | Truecaller Business API : Integration(VTS) | Integration with true caller | yes |  | 20
36 | 2026-02-03 |  |  | NFDC campaign | Voice campaign data | yes |  | 12
37 | 5/30/2026 |  | UI and Backend | Changes in report - madhya_kshetra | Changes in reporting | yes | approved by Gaurav sir | 15 |  | 2026-06-01
38 | 2026-08-05 |  | UI and Backend | RECL SLA report on Platform | SLA page for the user | yes | Approved | 3 |  | 2026-05-20